## known issues loged in JIRA
Sl No | Summary | Issue key | Issue id | Status | Assignee | Priority | Created | Reporter | Custom field (Severity) | Category
1 | Preview page is displaying blank after user fills the demographic and uploads document. | MOS-23101 | 33131 | To Do | Shashank.Agrawal | Medium | 2019-04-22 19:15 | usha.anandwade | Major | Inconsistent issue
2 | Validations are not taken care. | MOS-22802 | 32831 | To Do | Rudra.Tripathy | High | 2019-04-15 17:04 | Ashish.Rastogi | Major | Discussion WIP with CPU team and Rudra
3 | Applications are not getting Expired. | MOS-22485 | 32514 | Done | usha.anandwade | Medium | 2019-04-11 15:07 | usha.anandwade | Major | Known issue
4 | Two users are able to book an appointment for available one slot at same time from 2 different systems successfully .In the dashboard same appointment time is shown for both the users. | MOS-21769 | 31798 | Reopened | Kishan.Rathore2 | Medium | 2019-04-03 15:36 | usha.anandwade | Major | Known issue
5 | length in email address should be max(254) | MOS-21434 | 31463 | In Progress | Nagashree.Sudheendra | High | 2019-03-29 11:55 | Nagashree.Sudheendra | Major | Known issue
6 | Inappropriate pop up is displayed while uploading the document "PRG_PAM_CORE_011 Invalid document format supported for some valid document also" | MOS-23099 | 33129 | To Do | Gurdayal.Dhillon2 | Medium | 2019-04-22 18:42 | usha.anandwade | Major | Known issue
7 | Consent is not disappearing even after Auto logout | MOS-23087 | 33117 | To Do | Deepak.Choudhary | High | 2019-04-22 17:21 | Nagashree.Sudheendra | Major | Known issue
8 | AutologOut is not working when uploaded wrong document and error pops up | MOS-23086 | 33116 | To Do | Deepak.Choudhary | High | 2019-04-22 17:12 | Nagashree.Sudheendra | Major | Known issue
9 | View Acknowledgement for the applications from dashboard is breaking. Clicking on this is displaying a blank page to the user. | MOS-22762 | 32791 | Done | Agnitra.Banerjee2 | Medium | 2019-04-15 13:08 | usha.anandwade | Major | Known issue
10 | After discarding booked appointment,the slot associated to PRID is not getting available. | MOS-21571 | 31600 | Done | Ashish.Rastogi | High | 2019-04-01 12:06 | Ashish.Rastogi | Major | Known issue
11 | User is not getting any error code or error message by entering the invalid value for emailID field | MOS-18849 | 28878 | Done | Lavanya.Ranganathan | Medium | 2019-03-15 14:36 | Lavanya.Ranganathan | Major | Known issue
12 | Config:-I am able to rebook and cancel an appointment even if the appointment time is less than 20 min. | MOS-17478 | 27507 | Reopened | Kishan.Rathore2 | Medium | 2019-02-28 18:39 | Ashish.Rastogi | Major | Known issue
13 | User is able to book the Appointment for ld dates i.e., date less than today date | MOS-12161 | 22190 | Done | Lavanya.Ranganathan | Medium | 2018-12-28 12:34 | Lavanya.Ranganathan | Major | Known issue
14 | View document for the documents except pdf does not display the view of the document. | MOS-23104 | 33134 | To Do | Gurdayal.Dhillon2 | Medium | 2019-04-22 19:26 | usha.anandwade | Minor | Known issue
15 | Issue in the response of Cancel booking appointment after successful cancellation i.e., it is returning null for id and version key | MOS-23047 | 33077 | To Do | Ravi.Balaji | Medium | 2019-04-22 15:11 | Lavanya.Ranganathan | Not an issue | Pending feature
16 | while validating user with expired OTP it is not giving any proper error message. | MOS-21735 | 31764 | Done | Ashish.Rastogi | High | 2019-04-02 17:28 | Ashish.Rastogi | Minor | Known issue
17 | While validating user with invalid OTP not getting any proper error message. | MOS-21732 | 31761 | Done | Ashish.Rastogi | High | 2019-04-02 16:29 | Ashish.Rastogi | Minor | Known issue
18 | User is not getting any error code or error message by entering the invalid value for mobNum field | MOS-18848 | 28877 | Done | Lavanya.Ranganathan | Medium | 2019-03-15 14:25 | Lavanya.Ranganathan | Minor | Known issue
19 | User is getting success response Notification even by entering the preId which is doesn't exist in the system | MOS-18566 | 28595 | Done | Ravi.Balaji | Medium | 2019-03-14 18:40 | Lavanya.Ranganathan | Minor | Known issue
20 | After consume Pre-Registration Data System is not audit Registration center User ID[Reg Officer/Supervisor], RC ID | MOS-14127 | 24156 | Done | Ashish.Rastogi | Medium | 2019-02-05 19:00 | Ashish.Rastogi | Not an issue | Pending feature
21 | Invalid Response time by passing valid json request to the Booking Appointment API | MOS-12852 | 22881 | Done | Lavanya.Ranganathan | Medium | 2019-01-08 18:07 | Lavanya.Ranganathan | Minor | Known issue
22 | Mismatch in the Error code and Error message by passing invaid data for reqTime parameter of Booking Appointment API | MOS-12851 | 22880 | Done | Lavanya.Ranganathan | Medium | 2019-01-08 18:05 | Lavanya.Ranganathan | Minor | Known issue
23 | Invalid HTTP status code, Error code and Error message by passing empty value for reqTime parameter of Booking Appointment API | MOS-12843 | 22872 | Done | Lavanya.Ranganathan | Medium | 2019-01-08 18:00 | Lavanya.Ranganathan | Minor | Known issue
24 | for invalid request time (reqTime )it is not giving any error message. | MOS-12744 | 22773 | Done | Ashish.Rastogi | Medium | 2019-01-07 12:27 | Ashish.Rastogi | Minor | Known issue
25 | Invalid Response time for all the valid and Invalid request of Document Upload API | MOS-12326 | 22355 | Done | Lavanya.Ranganathan | Medium | 2018-12-31 17:38 | Lavanya.Ranganathan | Minor | Known issue
26 | Invalid HTTP Status code,error code,error message when user tries to send request by passing invalid value i.e.,date less than current date for reqTime key of Booking Appointment API | MOS-12111 | 22140 | Done | Ravi.Balaji | Medium | 2018-12-27 15:29 | Lavanya.Ranganathan | Minor | Known issue
27 | Issue in Response Time in Response body of Create Application API after sending the valid request | MOS-11980 | 22009 | Done | Ravi.Balaji | Medium | 2018-12-24 17:23 | Lavanya.Ranganathan | Minor | Known issue
28 | On Upload documents page, â€œSame asâ€ lists the current applicant name also. | MOS-23157 |  |  |  | Medium |  |  | Major | Known issue
29 | Applications deleted from dashboard are still listing under "Same As" document category. | MOS-23154 |  |  |  | Medium |  |  | Major | Known issue
30 | Notification service API returning the error code,error message along with the success message after success validation | MOS-23134 |  |  |  | Medium |  |  | Minor | Known issue
31 | Issue in the response of Cancel booking appointment after successful cancellation i.e., it is returning null for id and version key | MOS-23047 |  |  |  | Medium |  |  | Minor | Known issue
32 | Invalid HTTP Status code,error code,error message when user tries to send request by passing invalid value for langCode key of Create Pre-Registration API | MOS-12023 |  |  |  | Medium |  |  | Minor | Known issue
33 | Name with more characters is exceeding text boundary in dash board | MOS-23107 |  |  |  | Medium |  |  | Major | Known issue
34 | Mismatch in the error code and error message by passing invalid value for preregistration id | MOS-23221 |  |  |  | Medium |  |  | Minor | Known issue
35 | Issue in the wiki documentation | MOS-23167 |  |  |  | Medium |  |  | Minor | Known issue
36 | Names without POA displaying in same as in document upload | MOS-24119 |  |  |  | High |  |  | Major | Known issue
37 | When name selected without POA automatically next name is selected | MOS-24120 |  |  |  | High |  |  | Major | Known issue
38 | view of image file are displayed in document upload | MOS-24121 |  |  |  | High |  |  | Major | Known issue
39 | With invalid token i am able to perform action. | MOS-24099 |  |  |  | High |  |  | Major | Known issue
40 | while validating user with invalid userid getting wrong error message | MOS-24098 |  |  |  | High |  |  | Minor | Known issue
42 | Audit is not happening for document upload services | MOS-23758 |  |  |  | High |  |  | Major | Known issue
43 | After running sync master data for Availability slot is getting overwritten | MOS-23818 |  |  |  | High |  |  | Major | Known issue
44 | User is able to perform operation using other user's auth token | MOS-23720 |  |  |  | High |  |  | Major | Known issue
45 | Issue in Delete document by preregistration Id API ,returns null value for id,version,reqTime | MOS-24117 |  |  |  | High |  |  | Minor | Known issue

## Other Known issues (hidden)
Sl No
1 | Recommended centers will list only based on postal code as per design