## Sheet1
EPIC: Documentation | DOCUMENTATION TRACKER |  |  |  |  | Legend for current status
JIRA: MOS-13472 | Project: MOSIP | [5 empty] | Complete
| SPOC: Srijoni Sen | [5 empty] | Not Started\On hold due to Dependencies
| Architect: Shravan Poorigali | [5 empty] | WIP
Project Manager: Romila Mattu
User Type/ Audience (JIRA: Label) | Required Documentation (JIRA: Integrated Story/Component) | JIRA ID: Integrated Story | Document Artefacts (JIRA: Individual Story) | JIRA ID: Individual Story | Assigned To | Current Status | Priority | To be Published On | Additional Comments
Govt./Funders | Bluebook 1.0 | MOS-13479 | 1. Non-technical (Vision/Principles EG: Modularity, Security) – What aspect of MOSIP | MOS-13478 | Srijoni |  | High | Website
| Business Marketing Document | MOS-13481 | 1. Business Proposition and benefits of MOSIP (Why aspect of MOSIP) | MOS-13482 | Srijoni |  | High | Website
|  |  | 2. Success Stories | MOS-13484 | Srijoni |  | High | Website
|  |  | 3. Use Cases | MOS-13485 | Srijoni |  | High | Website
|  |  | 4. Clickable Prototypes of Functional Flow((Audio visual)) | MOS-13486 | Srijoni |  | High | Website
|  |  | 5. Data on existing reality | MOS-13487 | Srijoni |  | High | Website
| MOSIP Guidebook for Govt. | MOS-13489 | 1. Guidebook | MOS-13488 | Srijoni |  | Medium | Website
For Technical SI Guide (Commercial Implementation Partners) - Consultants/SI/ Device Manufacturers etc. | SI Guide | MOS-13490 | 1. SI-First Page Content: What (And What Not)/Why/How for SI (EG: Overview) | MOS-13491 | Mindtree |  | High | GitHub
|  |  | 2. Architecture Principles (Refer Platform Architecture doc) | MOS-13492 | Mindtree
|  |  | 3. Platform Standards (Refer WiKi page – EG: i18n, Device Standards) | MOS-13493 | Mindtree
|  |  | 4. Functional requirement Specifications | MOS-13494 | Mindtree
|  |  | 5. Non-Functional Requirement Specifications | MOS-13495 | Mindtree
|  |  | 6. Design and Principles (API Specs, Device Specs etc.) | MOS-13497 | Mindtree
|  |  | 7. Deployment Guide a.Guide on deployment (Used by SI/ Device manufacturers) | MOS-13498 | Mindtree |  | High | GitHub
|  |  | 8. Infrastructure Recommendations (Used by SI/ Device manufacturers) | MOS-13499
|  |  | 9. Setup Manual: Guide to Pre-registration | MOS-13500 | Mindtree |  | High | GitHub
|  |  | 10. Setup Manual: Guide to Registration Client Application | MOS-13501 | Mindtree |  | High
|  |  | 11. Setup Manual: Guide to Setup and initiate platform > Admin portal (Data, Device, User Setup) > Backend Setup (ID Definition Schema, Configs, others) | MOS-13502 | Mindtree |  | High
|  |  | 12. Clickable Prototypes to Functional Flow | MOS-13504 | Mindtree
|  |  | 13. Technical Overview: Platform Architecture | MOS-13505 | Mindtree |  | High | GitHub
| Roadmap | MOS-13506 | 1. Details on Releases of v1 | MOS-13507 | Mindtree |  | High | GitHub
|  |  | 2. Known Issues of v1 | MOS-13508 | Mindtree
|  |  | 3. v2/v3 Features | MOS-13509 | Mindtree
| Developer Documents | MOS-13510 | 1. Roadmap, Current Issues (JIRA), Priority, Contribution Guide | MOS-13511 | TBD |  | High | TBD
|  |  | 2. API Specifications | MOS-13512 | TBD |  | High
|  |  | 3. Test Scripts, Test Cases | MOS-13513 | TBD |  | High
| Architecture | MOS-13521 | 1. Platform Architecture | MOS-13529 | Mindtree |  | High | GitHub
For Industry Experts | Architecture | MOS-13530 | 1. MOSIP Technology Roadmap | MOS-13531 | Mindtree |  | Medium | GitHub
|  |  | 2. MOSIP Open source organization and processes | MOS-13532 | Mindtree |  | Medium | GitHub
|  |  | 3. Tools and Technology | MOS-13533 | Mindtree |  | Medium | GitHub
|  |  | 4. Architecture Document | MOS-13534 | Mindtree |  | Medium | GitHub
For Open Source Contributors and MOSIP Model | Open Source Community Docs | MOS-13535 | 1. Introduction to MOSIP (Details to be defined) | MOS-13536 | Mindtree |  | Medium | GitHub
|  |  | 2. Governance (Details to be defined) | MOS-13537 | Mindtree - TBD |  | Medium | GitHub
|  |  | 3. Community Guidelines – Expectation and Recognition | MOS-13538 | Mindtree |  | Medium | GitHub
|  |  | 4. Help Needed Areas/Areas of Development | MOS-13539 | Mindtree |  | Medium | GitHub