## Effort Summary-Timelines
Effort Summary & Timelines
Page/Section | Effort (PDs) | UX Delivery Timeline | UX Approval Status | Comments (PDF to be attached)
General | 7.5 | TBA | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Login | 3.75 | 2019-06-03 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Homepage | 6.25 | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Consent | 0.25 | 2019-05-31 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Header + Footer |  | 2019-06-03 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Demographic | 10 | 2019-06-04 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Stepper | 1 | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Document Upload | 7.75 | 2019-06-04 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Preview | 1.75 | 2019-05-31 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Book Appointment |  | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Center Selection | 2.6 | 2019-06-06 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Time Selection | 3.25 | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Acknowledgement | 1 | 2019-05-31 | Approved | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
ManualLogout |  | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Empty State |  | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Discard |  | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Logout |  | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
GoM specific Demo page |  | 2019-06-10 | WIP | https://github.com/mosip/mosip/tree/master/docs/requirements/UXEnhancement/Pre-registration
Total Effort | 45.1
Note on C4: MINDTREE: To be revised based on latest changes
Note on E7: MINDTREE: Refer Comments on email
Note on E11: MINDTREE: Refer Comments on email
Note on E14: MINDTREE: Refer Comments on email
Note on E16: MINDTREE: Refer Comments on email
Note on E18: MINDTREE: Refer Comments on email
Note on E19: MINDTREE: Refer Comments on email
Note on E20: MINDTREE: Refer Comments on email
Note on E21: MINDTREE: Refer Comments on email
Note on E22: MINDTREE: Refer Comments on email

## General
S.No. | Change - Jira Ids | Efforts (in pd) | Comments
1 | MOS-24695 - UI Enhancement - IV & V: Provide a Cancel button and Cross button in all dialog boxes across Pre-registration | 3 | Functionality impact and css impact ( 3 is tentative)
2 | MOS-24691 - UI Enhancement - IV & V: Fix the header of the Pre-registration UI application once logged in | 1 | NA
3 | MOS-24679 - UI Enhancement - IV & V: Trigger "User Blocked" message in UI if user enters OTP incorrectly x times, as configured | 2.5 | Functionality impact and css impact, global configuration changes)
4 | MOS-24678 - UI Enhancement - IV & V: Provide a warning message prior to logging out a user on click of "Logout" | 1 | NA
5 | Update Verbiage of Messages across Pre-registration to first eprson instead of third person - Instead of 'Applicant should login with…", replace with "Please login with.." - Directly addressing the individual
6 | Icons across pre-registration to be more innovative
7 | Remove headings from all pages and leverage the space to provide i icon - On demand give instructions i. Consider placing the headings vertically on the left
8 | Overall indicate which aspects are clickable and which are not (EG: Hand icon on hovering on option or highlighting the option)
9 | Overall - Approach of headers for dialog boxes to be changed as per "Additional Email/SMS Ack" in Ack. Page
10 | Any clickable action should have tooltip text across the application
| Total Effort | 7.5

## Login
S.No. | Change | Effort (PDs) | Comments
1 | Login with border and translucent color | 3 | NA
2 | Remove text – Quick and Easy Steps – Accordingly space out and align the Login card | 0.75 | NA
3 | Selection of text box to have pink color |  | NA
4 | Re-consider reversal of "Resend" button and "Valid for x mins" |  | NA
| Total Effort | 3.75

## Homepage
S.No. | Change | Effort (PDs) | Comments
1 | Modify / Book button CSS | 0.25 | NA
2 | Card styling | 6 | NA
3 | Pagination | 0 | Not taking into consideration as it has functionality as well as css changes, and pagination is only taken care at api level)
4 | layout Update as per VDs: a. Provide wireframes with display of 1 card and 8 cards/maximum number in one view b. Remove the labels within the card (Remove: Pre-registration ID, Applicant Name, Appointment) and use icons c. On zooming, the page does not become responsive but is provided with a horizontal scroll
5 | Functional change: Sequence of displaying appointments in homepage - Pending App > Booked (Latest app first)
6 | Functional change: Each card to also have the Center details displaying - If status = Booked
7 | Text "My Application" if only one and "My Applications" if many, should change based on number of application(s)
| Total Effort | 6.25

## EmptyState
S.No. | Change | Effort (PDs) | Comments
1 | Include new page - Redirect user to this page, when no applications exist and on first login |  | NA
| Total Effort | 0

## Stepper
S.No. | Change | Effort (PDs) | Comments
1 | Icon change and padding | 1 | NA
2 | Clickable stepper(Top navigation) and color based approach with supplementary text/status a. Activities to be split to two steps: Form Filling (Incl. Demo Data, Doc Upload and Preview) and Book Appointment (Incl. Location, Time Slot, Ack.) b. Once user opts to Book Appointment - Demographic, Doc Upload and Preview should not be viewable c. Update of Demo and Docs should be possible only from dashboard |  | NA
| Total Effort | 1

## Consent
S.No. | Change | Effort (PDs) | Comments
1 | Title, Sub title, content alignment color changes | 0.25 | NA
2 | "Accept" button should be enabled only on click of checkbox |  | NA
3 | Color to indicate "in focus" field as per VDs |  | NA
| Total Effort | 0.25

## Header + Footer
S.No. | Change | Effort (PDs) | Comments
1 | Header + Footer with border and translucent color | 3 | NA
2 | Footer after Login across all pages should be with border and translucent coloring | 0.75 | NA
NA
NA
| Total Effort | 3.75

## Demographic
S.No. | Change | Effort (PDs) | Comments
1 | Indication of Mandatory and Optional fields
2 | - Keyboard Icon In Every Text field is not required - Icon to be placed as per VD (center) - Virtual Keyboard to be brought up on demand (click) only and should disappear on next click - It should also have a cross "x" button to close the keyboard when not required - It should not toggle while navigating from one text field to another - Virtual Keyboard should be prompted for numeric fields also (Including email) - Virtual Keybaord should be standard with special characters included (@...) - This will further be browser dependent (Current full size keyboard) | 0.75 | Functionality not included that is on click of keyboard icon key board should appear
3 | Padding and alignment of text field | 0.75 | As per the older location hierarchy (with drop down for all the location and old position of fields)
3 | Padding, alignment and colour of action buttons | 0.25 | NA
4 | Toggle button styling | 0.25 | NA
5 | Update to non-editable fields | 8 | NA
6 | For 30Jun: Address Structure: - Move Address L1/2/3 below Province, region, layout etc - Padding, alignment to be accommodated - Non-editable fields on the right side should not have dropdowns and buttons (Retain labels and underline)
7 | Post 30Jun: Implement Location Hierarchy changes as per latest GoM location hierarchy
8 | Text - "Please provide your personal details" and text for "Age/DoB" field should be provided within an i icon
9 | Re-evaluate depiction of address structure so that scroll can be reduced
10 | Display the indicative text on focus on Age/DoB
| Total Effort | 10

## DocUpload
S.No. | Change | Effort (PDs) | Comments
1 | Layout change: a. When a document is uploaded against one of the proof type then the green tick will show to indicate that document is uploaded. - Once a Doc is uploaded, system should not allow chaning the selection of the "Doc Type" uploaded b. If the user doesn’t upload anything against a proof type then the Browse option with "Not Uploaded" text will appear c. On click of Upload icon, the doc should be attached and the filename should appear d. The Upload function should be removed when a document is present and icon should change to green tick e. Modify option is not required f. The view and remove actions will also show only when the document is present g. On click of Remove, the line moves back to original state with Browse button h. The file type and file size should be placed on top i. The view and remove icons needn’t be spaced to the complete right j. Same As option: i. For POA - Revised layout | 3 | N/A
2 | Max file size - Position change | 0.5 | N/A
3 | Dropdown - css change | 0.5 | N/A
4 | View - Placement change | 0.5 | N/A
5 | Remove button functionality | 1
6 | Include Remove button | 0.5 | positioning and css
7 | Include Tick icon | 0.25 | css changes
8 | Include Tick functionality | 0.5
9 | Same As - Alignment | 1 | CSS and Position changes
| Total Effort | 7.75

## Preview
S.No. | Change | Effort (PDs) | Comments
1 | Placement of Modify button and border change | 1 | NA
2 | Field value association | 0.5 | NA
3 | Padding, alignment and colour of action buttons | 0.25 | NA
4 | a. Replace question mark icon with informative icon (i) b. Centre spacing is too wide: i. Add "Modify" option in the centre ii. Consider Centre aligning the text in each language section c. Consider keeping the page non-scrollable d. Move CNIE/EC Number to Personal Info section e. Icons to be updated as per VDs
| Total Effort | 1.75

## Center Selection
S.No. | Change | Effort (PDs) | Comments
1 | Border Box | 1
2 | Map Alignment | 0.25
3 | Center selection card | 0.25
4 | Drop down colour change and search icon alignment | 0.5
5 | Padding, alignment and colour of action buttons | 0.5
6 | Recommended Center Underline | 0.1
7 | a. Merge Centre selection and time selection pages to one page – As two tabs within one page: “Center Selection” and “Time Selection” b. Search Centre Tab: i. Revised layout: The 3 search options should be tab based 1. Move Search option to be aligned with the other two options 2. Search result count can be moved below the 3 options ii. Update verbiage of Recommended Centres to Recommended Centres iii. Provide scroll post view of 5 centres
8 | Indicative text on top - Specific to Location as per VD
| Total Effort | 2.6

## Time Selection
S.No. | Change | Effort (PDs) | Comments
1 | Booked Applicant should be always shown in the side bar | 3 | Includes Functionality and CSS changes (3 days is tentative can take more days to implement)
2 | Padding, alignment and colour of action buttons | 0.25 | NA
3 | Layout Change: i. Revised layout of date cards for availability - Month name to be placed outside the card, above the first day of respective month ii. Morning and Afternoon – Make the tabs more evident iii. Revised layout for depicting number of applicants booked and number of available slots, per time slot - Card layout with number of slots booked to be removed iv. Right action navigation pane 1. Rename sections: Available Applicants to Pending Booking and Booked 2. Pending: a. Allow action (+ icon) b. Display number of applicants pending booking c. Tooltip for + icon 3. Booked: a. Allow action (x icon) b. Display number of applicants for whom slots are alloted c. Display each individual’s name with the relevant time slot details (Remove morning/evening from details) d. Tooltip for - icon
4 | If no applicants are
5 | Message on top - To be updated as per VD
| Total Effort | 3.25

## Acknowledgement
S.No. | Change | Effort (PDs) | Comments
1 | QR code alignment | 0.25 | NA
2 | Padding, alignment and colour of action buttons | 0.25 | NA
3 | Text, styling | 0.5 | NA
4 | a. Reduce the number of lines under Guidelines b. Remove “Add Another” option c. Rename “Send SMS/Email” to “Send to Additional Email/SMS” or something on similar lines i. Same to reflect within the dialog box
5 | Ack. Success Message change as per VDs
| Total Effort | 1

## ManualLogout
S.No. | Change | Effort (PDs) | Comments
1 | Provide a warning message to user before logout |  | NA
| Total Effort | 0

## Discard
S.No. | Change | Effort (PDs) | Comments
1 | Discard appointment option should be greyed out if no appointment exists |  | NA
| Total Effort | 0