## MOSIP_QueryLog_TechBoard
MOSIP - QUERY LOG_TechBoard
# | Date of Query | Query Type | Reference (User Story/Document, Version, Section, REQ ID, Page) | Status | Module | Query | Query By | Owner | Clarification | Clarified By | Query Closure Date | Remarks
26 | 2018-04-06 | Functional | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-EC-100-R12 | Discussed - Action item pending | Registration | Photo Capture: Is MOSIP expected to validate that the photo is compliant to ICAO guidelines? The ICAO guidelines state, for example, that the photo must - have a plain, light-coloured background - have the face take up 70-80% of the photograph - show the subject looking directly at the camera, etc. Reference: https://www.icao.int/Security/mrtd/Downloads/Technical%20Reports/Annex_A-Photograph_Guidelines.pdf |  |  | - Morocco will use high resolution DSLR cameras - Standards and validation rules should be configurable+pluggable - MOSIP default should be ICAO. Also code for one more standard besides ICAO - The algorithms for each validation should be pluggable - Reconfirm with Shravan. - MT to recommend guidelines for ICAO and another standard (EG:Webcam) as part of MVP | Anadi | 2018-09-19
51 | 2018-04-06 | Functional | - Aadhaar Master List of Requirements | Discussed - Action item pending | Registration Processor | EY-EID Number Mapping: The Aadhar requirements list available with Mindtree contains the following item. "Add a barcode containing the EID on aadhaar letter visible in envelope window. This is to facilitate capturing of EID for returned letters at contact centre. This will remove dependency on scanning EY barcode and having correct EY-EID mapping availability." What is EY? Please elucidate this requirement. |  |  | - MOSIP to provision the mapping of RID with both print and postal tracking number - Printing and postal are two separate systems with two codes. Note: Integrations with external systems - TBD with Shravan/Anadi | Anadi | 2018-09-20
53 | 2018-04-06 | Functional | - Aadhaar Master List of Requirements | Discussed - Action item pending | Registration Processor | On-Hold Workflow: 1. What is the default expected behavior with respect to keeping an enrolment packet on hold? Example: Auto re-submission if the awaiting condition is met. 2. What is the system behavior when on-hold packets have crossed their defined wait period? Are they rejected? |  |  | - This should be a configurable workflow, considering re-submission/reject - Shravan to check feasibility based on design | Anadi | 2018-09-20
55 | 2018-04-06 | Functional | - Aadhaar Master List of Requirements | Discussed - Action item pending | Registration Processor | Manual Dedupe: What is the default process preferred in terms of auto-approve/auto-reject during deduplication? Is the following correct: - If a duplicate is not identified, auto-approve the application. - If a duplicate is identified, the system should determine the % match value. If this is below a certain threshold, auto-reject. Else place in a queue for manual adjudication. - If no action has been taken on an item in the manual adjudication queue beyind a defined period, auto-reject the application. |  |  | - This should be a configurable workflow - Shravan to check feasibility based on design | Anadi | 2018-09-20
56 | 2018-04-06 | Functional | - Aadhaar Master List of Requirements | Discussed - Action item pending | Registration Processor | T & T File/Booking File: The Aadhar requirements list available with Mindtree contains the following item. "Enhancements required in the T&T file and Booking file processing: 1) To remove certain validations like booking file name check 2) To add a unique key like EID+Barcode check 3) Certain files with missing EIDs or invalid format. " What are T&T files and Booking files? Please elucidate this requirement. |  |  | - Anadi/Shrikant to get back | Anadi | 2018-09-20
76 | 2018-04-11 | Functional | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R4 | Clarified & Closed | ID Authentication | Biometric Authentication Service: 1. A TSP should be able to authenticate an applicant using biometrics. Can different agencies within a country have different assurance levels (For example, banks having different match thresholds compared to telecom service providers)? 2. Will defining biometric assurance levels per TSP be in MOSIP scope? 3. What should be the approach to best finger detection during authentication? The suggested approach is to determine the fingerprint quality score and match score, and use them come up with a composite score to identify the best finger. |  |  | - No this is not required at TSP level but only at Country level | Anadi | 2018-09-19
79 | 2018-08-06 | Functional | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R8 | Discussed - Action item pending | ID Authentication | Local Language Support for Demographic Authentication: MOSIP should be able to do a phonetic match provided the authentication request contains data in one of the two languages in which resident data is stored. - What is the extent of customization required for this feature? Should MOSIP codify the rules for phonetic matching? - Should MOSIP provide the ability to configure the match level? |  |  | - MOSIP should have the ability to consume a library (Language based) > MT team to analyze Soundex > Anadi to liaise with Balasundar | Anadi | 2018-09-19
80 | 2018-04-11 | Technical | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R10 | Discussed - Action item pending | ID Authentication | Authentication Performance: For Simple and Advanced Authentication Performance, Mindtree will provide benchmarks under test conditions and based on commodity hardware (Standard off the shelf hardware). Please confirm that our understanding above is correct. |  |  | -MT to provide H/W specifications on CPU ,Ram usage,etc and Virtual machine specifications . - Shravan to analyse and provide data on this | Anadi | 2018-09-20
81 | 2018-04-11 | Technical | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R12 | Discussed - Action item pending | ID Authentication | Address Verification Performance: Why is there a specific performance requirement to support address verification? This would be a part of simple and advanced authentication performanace as noted above. Regardless, Mindtree will provide benchmarks under test conditions and based on commodity hardware (Standard off the shelf hardware). Please confirm that our understanding above is correct. |  |  | -MT to provide H/w specifications on CPU ,Ram usage, etc and Virtual machine specifications. -MT also to provide the H/w quantity to be supported - Shravan to analyse and provide data on this | Anadi | 2018-09-20
82 | 2018-04-11 | Technical | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R13/14/15/16/17/18 | Discussed - Action item pending | ID Authentication | Scalability and Availability Requirements: The stated requirements are: 1. Horizontal Scalability 2. High Availability within a DC 3. High Availability Across Multiple DCs 4. Ability to Partition Data Across Servers and DCs 5. Ability to Load-balance Across Servers and DCs Mindtree proposes to implement the following to meet the above requirements: - Ensure Clustering concept is enforced - Ensure Data sharding and Replication is enforced Please validate if anything else needs to be considered. |  |  | - Anadi to get back in discussion with Shravan, based on aadhaar | Anadi | 2018-09-20
84 | 2018-04-11 | Technical | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R19/20 | Discussed - Action item pending | ID Authentication | Security & Auditing: 1. Protecting from Unauthorized Clients 2. Protecting from Request Tampering Mindtree proposes to implement the following to meet the above requirements: - Reject unauthroized API Data request call through encryption - Ensure Session Handling is enforced - Ensure Hash is verified for each authentication request Please validate if anything else needs to be considered. |  |  | - Mindtree to facilitate device spec setup/config and security features for registration - MT to provide specific details on how Devices Security will be met for Registration and ID-Authentication - Authentication Client is not considered as part of MOSIP - Anadi to seek clarification on auth client | Anadi | 2018-09-20
86 | 2018-04-11 | Functional | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R22 | Clarified & Closed | ID Authentication | Ability to Retain Audit Trails for Prescribed Days: The states requirement is: 1. Cron jobs to compliancy in regular intervals. Mindtree proposes to implement the following to meet the above requirement: - Ensure a cron job purges the audit data based on configuration. Please validate if anything else needs to be considered. |  |  | - There should be two stores: > A near store which will store 2-3 days of data > store to store the logs for a longer duration | Anadi | 2018-09-20
88 | 2018-04-11 | Functional | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-IA-100-R25/26 | Discussed - Action item pending | ID Authentication | Sync data across DCs: How different are the two requirements: - Ability to Synchronize across DCs, and - Ability to Guarantee Change Propagation? Mindtree proposes to implement the following to meet the above requirements: - Ensure Data sharding and Replication is enforced Please validate if anything else needs to be considered. |  |  | - Multiple instances to be synced programatically/database wise based on configuration - When data gets updated in one DC, it gets synced to the other - This should be covered as part of design - Shravan/Anadi | Anadi | 2018-09-20
93 | 2018-04-11 | Functional | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 - REQ-EC-100-R14/15 | Clarified & Closed | Application Requirement | Integration with SDK - Biometrics Quality Check Engine: 1. Confirm SDK support will be provided by SDK vendor. 2. Confirm Segmentation will be done by MOSIP using the same SDK. |  |  | - MOSIP should provide an interface to connect to biometrics service provider and should be part of MVP | Anadi | 2018-09-20
94 | 2018-04-11 | Functional | - MOSIP_UserStoryBacklog_Tracker_v0.13 - PwC_RNP Morocco_High Level FRS_v1.1_12 Jan 2018 | Discussed - Action item pending | Application Requirement | Integration: For all integration requirements, is MOSIP required to provide an admin console? |  |  | - MOSIP should provide a config console which is to be defined using the master configuration file - Anadi to discuss further with Shravan | Anadi | 2018-09-20
103 | 2018-08-06 | Functional | MOSIP_Product Backlog_Consolidated_Module-Component-Features_v1 | Discussed - Action item pending | Registration | Download enrolment client application: MOSIP will provide the ability to run the client application from a dongle. Should MOSIP also support download and install of the client application on the enrolment machine? |  |  | - MOSIP should support running the Registration client application through dongle only (read only), from Security standpoint - Encrypted registration packets to be subsequently stored in the machine - Aadhaar requirement for dongle and storage of packets in hard disk vs USB - Shrikant to discuss with Pramod - Registration software update process on dongle - Anadi/Krishnan to discuss with Shravan | Anadi | 2018-09-19
124 | 2018-08-06 | Functional | MOSIP_Product Backlog_Consolidated_Module-Component-Features_v1 | Discussed - Action item pending | ID Authentication | Static Token instead of UIN/VID for Authentication Should MOSIP support demographic authentication using Token, in addition to authentication with UIN/VID? - The authentication request will contain the Demographic details and Token for the resident for that TSP; - Response returns Yes/No. Reference: https://uidai.gov.in/images/resource/UIDAI_Circular_11012018.pdf, point 13(e). |  |  | - This can be on-hold - Anadi/Shrikant to get back | Anadi | 2018-09-20
135 | 2018-08-10 | Functional | -RFP_Selection of SI_NPR_Morocco volume I v5.6 | Discussed - Action item pending | Registration | Lifeless finger detection: Page 9 of the RFP for SI states: "Additionally provisions of lifeless finger detection, biometric authentication, two factor authentication, and PKI based encryption techniques will be implemented." Please confirm that lifeless finger detection is not MOSIP scope. |  |  | TBD with Sanjay - Anadi to confirm - Biometric Service Provider (BSP) to provide this feature - This should be performed on client side by BSP and server side by ABIS - MOSIP to provision ability to configure: > Select a BSP from multiple BSP > Configure threshold levels | Anadi | 2018-09-19
137 | 2018-08-10 | Functional | -RFP_Selection of SI_NPR_Morocco volume I v5.6 | Discussed - Action item pending | Registration Processor/ ID Authentication | Biometric updates: Page 42 of the RFP for SI states: "RNP may maintain a threshold for quality of biometrics and in case the quality of captured biometrics does not satisfy the threshold, the RNP may intimate the resident to update their biometrics." Does MOSIP scope include the requirement to intimate a resident to update their biometrics if quality is below threshold? As we understand, this can be triggered if a high NFIQ score is identified during authentication but the authentication fails. |  |  | - MOSIP to have the ability to configure scenarios when individual to be notified (Through a periodic job) to update biometrics: > Child turns 5/15 > Authentication cosistently fails beyond x (configurable) times of being below the defined NFIQ threshold (configurable) - MT to analyze and recommend algorithm (Come up with an algorithm using quality of biometric at registration and quality of match at authentication) | Anadi | 2018-09-19
141 | 2018-08-13 | Functional | PwC_RNP Morocco_L3_Solution Overview_ver 3.4 - Mindtree.pdf | Discussed - Action item pending | Registration Processor | Seeding UIN to Government Gateway: Please confirm the below is not in MOSIP scope - "The UIN number shall be seeded through a Government gateway into various government database to provide direct benefit transfers, and removal of any ghost or duplicate entries." (Morocco Req Doc _ PG: 19) |  |  | - This is not in MOSIP scope - Anadi to get back | Anadi | 2018-09-20
142 | 2018-08-13 | Functional | MOSIP_UserStoryBacklog_Tracker_v0.19.7.xlsx | Discussed - Action item pending | ID Authentication | Consent Management: Please confirm the following - 1. Consent Management (lock/unlock biometrics, authentication, KYC/individual data sharing) will not be in MOSIP scope 2. MOSIP will provide services for below features and not provide the reference implementation for resident services portal: > UIN Status tracking, Download/Retrieve e-UIN, Update UIN data, Generate VID, Generate Static PIN, View Authentication History |  |  | - Anadi/Shrikant to get back | Anadi | 2018-09-20
143 | 2018-08-13 | Functional | MOSIP_UserStoryBacklog_Tracker_v0.19.7.xlsx | Discussed - Action item pending | ID Authentication | TSP Devices: Do TSP devices need to be registered in MOSIP before they can be used for authentication? Devices in this context are only biometric devices and not other devices like POS,terminals, PCs etc used for authentication? |  |  | - Mindtree to facilitate device spec setup, registration, and security features for registration -MT to provide specific details on how Devices Security will be met for Registration and ID-Authentication - Authentication Client is not considered as part of MOSIP - Anadi to seek clarification on auth client | Anadi | 2018-09-20
153 | 2018-08-17 | Functional | aadhaar_authentication_api_2_5 | Discussed - Action item pending | ID Authentication | Demographic Authentication: In Aadhaar one API holds all input parameters of Demo, Bio, OTP And PIN as optional parameters. If mutiple demo parameters are used for authentication should the Authentication Response be a 'Yes' only if every individual authentication is a success? What are the threshold levels for matchness when there are multiple parameters? Approach for multi-factor authentication to be conveyed to tech board. |  |  | - Request and Response pattern/design for individual/multifactor authentication is ok. Currently,quality Threshold level for biometrics should be the same for all TSPs, as configured by a Country admin - Should MOSIP support TSP level config of threshold matchness for Biometrics? - Anadi/Shrikant to get back | Anadi | 2018-09-20
156 | 2018-08-17 | Functional | aadhaar_authentication_api_2_5 | Discussed - Action item pending | ID Authentication | Biometric based Authentication: Will the TSP generate minutiae for the Fingerprint/IRIS/Facial images sent as part of authentication request? |  |  | - Authentication Client is not considered as part of MOSIP - Anadi to seek clarification on auth client | Anadi | 2018-09-20
170 | 2018-08-28 | Functional | MOSIP_UserStoryBacklog_Tracker_v0.19.7.xlsx | Clarified & Closed | Registration Processor | Face deduplication: Is there a requirement for face deduplication during packet processing? |  |  | - MOSIP should provide an interface to connect to face deduplication, iris and finger print service provider and should be part of MVP | Anadi | 2018-09-20
177 | 2018-09-18 | Functional | MOSIP_UserStoryBacklog_Tracker_v0.19.7.xlsx | Discussed - Action item pending | Registration Processor | Demographic Dedpue: What is the algorithm MOSIP is expected to adopt for Demographic Dedupe? |  |  | - The logic should be developed as part of MOSIP - Anadi to get back on aadhaar documentation | Anadi | 2018-09-20
178 | 2018-09-19 | Functional | MOSIP_UserStoryBacklog_Tracker_v0.19.7.xlsx | Pending | Registration | Login: Should login of RO/SPVR with finger print and Iris be scoped within MVP? |  |  | - Yes. MOSIP should support two/multi-factor authentication based login as part of MVP, both for Login to commence enrolment and Operator Authentication at the end of each enrolment | Anadi | 2018-09-19
179 | 2018-09-19 | Functional | MOSIP_UserStoryBacklog_Tracker_v0.19.7.xlsx | Clarified & Closed | ID Authentication | Static PIN Authentication: Should Static PIN based Authentication be part of MVP? |  |  | - This should be considered as part of MVP | Anadi | 2018-09-20
180 | 2018-09-19 | Functional | MOSIP_UserStoryBacklog_Tracker_v0.19.7.xlsx | Discussed - Action item pending | ID Authentication | Tokenisation: Should Tokenisation be part of MVP? |  |  | - This can be on-hold - Anadi/Shrikant to get back | Anadi | 2018-09-20
181 | 2018-09-20 | Functional | Tech board clarification session_20Sep18 | Pending | Application Requirement | Device Specs setup/Integration/VDM/Security Features: Requirement and approach to the above to be discussed |  |  | - Anadi/Shravan to discuss
183 | 2018-09-25 | Functional | aadhaar_authentication_api_2_5 | Pending | ID Authentication | License Keys for TSP In addition to AUA and ASA codes, these entities are issued license keys. What is the purpose of having these license keys issued as we have codes to identify these entities? |  |  | Anadi to get back.
190 | 2018-10-03 | Functional | aadhaar_authentication_api_2_5 | Pending | ID Authentication | Authentication Response Info: As part of the response when mutiple parameters are used for authentication, MOSIP sends the attribute (say Name/Address) used to generate the auth response. However we are not sending the match value,match strategy and language used for matching. Please validate. Aadhaar reference : lang, pi-ms, pi-mv , pi-lmv, pa-ms, pa-lmv, pfa-ms, pfa-mv, pfa-lmv parameters are part of info element of the response.
191 | 2018-10-04 | Functional | Morocco FRS Annexure D | Clarified & Closed | Registration | Registration Fields: The following are from the the Morocco FRS: "PIN Number - mandatory for new born child registered using Electronic Child Registration System" How will the Registration Client know whether the individual was registered with the ECR system as a new born, thereby making this field mandatory? "Residence Proof - mandatory for foreigners" This is listed under demographic data and not under document uploads. Is this then meant to be just a text entry field, and what is expected to be entered here?
195 | 2018-10-08 | Functional | aadhaar_ekyc_api_2_5 | Pending | ID Authentication | Parameters in e-KYC api: Code parameter in Aadhaar: As per Aadhaar API,this is a unique alphanumeric response code for e-KYC API having maximum length 40. AUA is expected to store this for future reference for handling any disputes. Aadhaar KYC server will retain e-KYC trail only for a short period of time as per UIDAI policy. What is the purpose of the parameter? TTL in Aadhaar: As per Aadhaar API,"Time To Live” for demographic data within AUA system. AUAs may not use the resident data obtained through this API beyond this time and should use this API to obtain latest resident data. Should this be configurable for a country? How was this determined in Aadhaar?
198 | 2018-10-08 | Functional | aadhaar_ekyc_api_2_5 | Pending | ID Authentication | Encryption of e-KYC Response: MOSIP will be encrypting the PII data as part of e-KYC response and will not be encrypting other parameters like Authentication success/failure, error code etc similar to Aadhaar. Please validate MOSIP will also not encrypt other type of authentication (OTP/BIO/DEMO/STATIC PIN) responses. Please validate. In the FRS document from Morocco, we believe the response encryption is with regards to PII data of response e-KYC. Please validate.
199 | 2018-10-09 | Functional | aadhaar_ekyc_api_2_5 | Pending | ID Authentication | Parameters in e-KYC api: 1. As per Aadhaar API the parameter 'de' is a flag indicating if KUA is delegating decryption to ASA Why should the ASA be allowed to decrypt the response? MOSIP will not be supporting this. Please validate 2. Why does Aadhaar have a seperate API for e-KYC instead of having a flag for e-KYC in Aadhaar Authentication API?
200 | 2018-10-17 | Functional | aadhaar_ekyc_api_2_5 | Pending | ID Authentication | Design of eKYC api: Why does Aadhaar have a seperate API for e-KYC instead of having a flag for e-KYC in Aadhaar Authentication API? | 1. This could be due to E-KYC involving exposure of information. MOSIP should also have a separate API TBD with Anadi for clarity on the reason | Shrikant | 1. This could be due to E-KYC involving exposure of information. MOSIP should also have a separate API TBD with Anadi for clarity on the reason
201 | 2018-10-25 | Functional | aadhaar_authentication_api_2_5 | Pending | ID Authentication | TSP License Keys 1. How are license keys for AUA and ASA generated and maintained in Aadhaar? 2. Are authentication type permissions and eKYC permissions tagged to AUA license keys in Aadhaar? What is the expectation from MOSIP?
202 | 2018-10-25 | Functional | aadhaar_authentication_api_2_5 | Pending | ID Authentication | Session Keys What is the guidelines for AUA to generate the session keys. What is the standard in Aadhaar?
203 | 2018-10-26 | Functional | User Story - MOS-1064 Query Log Query - MOS-8589 | Pending | Registration Processor | Demo De-Duplication In Demographic De-duplication, we are supposed to check the demographic details of the packets with other successfully processed packets stored in DataStore/DataBase. 1. As we are storing Demographic Data in encrypted format in Database; How are we going to perform Demographic Deduplication for the Packets on Encrypted Data? 2. How is Data Stored in Aadhaar for Demo Dedupe?
Note on A2: Vivek Srinivasan: The numbers correspond to serial numbers in the Mindtree master query log.