## Features
Sl No. | Modules | Features | JIRA IDs | Priority | Dependency | Vendor | Status |  | Dependency TBM By | Est. (CUT) | Dev Complete | Est.(Func Test) | Test Complete | People | Comments
1 | Registration Client | MDM Integration | MOS-22410 | High |  |  | Dev Completed | Issue - Unable to Capture Low Quality Biometrics | NA | NA | NA | 0.5 | Sprint 19 | Sravan | Completed with SyncByte
2 | Registration Client | New Registration – Biometric Data Capture | NA | High |  |  | Dev Completed |  | NA | NA | NA | 3 | Sprint 19 | Sravan | Completed with SyncByte
3 | Registration Client | On-Boarding of Operator | MOS-19001, MOS-28791 | High | Sl No. - 23 (IDA) |  | In-Progress | Internal Auth API is not developed due to Vendor dependency | 16th Oct | 2 | Sprint 20 | 2 | Sprint 21 | Taleev
4 | Registration Client | Update UIN – Biometric Data Capture | MOS-15998 | High |  |  | Dev Completed | Issue - Unable to Process Update Request in ABIS | NA | NA | NA | 3 | Sprint 19 | Sravan | Completed with SyncByte
5 | Registration Client | Lost UIN – Biometric Data Capture | NA | High |  |  | Dev Completed |  | NA | NA | NA | 2 | Sprint 19 | Usha | Completed with SyncByte
6 | Registration Client | Parent – Biometrics Data Capture | MOS-21701 | High | Sl No. - 27 (Reg Proc - IDA) |  | Not Yet Integrated | Internal Auth API is not developed due to Vendor dependency | 16th Oct | 3 | Sprint 20 | 2 | Sprint 21 | Taleev | Dev Can Start Now … We can do integration Post 16th Oct
7 | Registration Client | Operator Authentication | MOS-28792, MOS-12185, MOS-1334 | Medium | SDK | Tech5 | Not Yet Integrated | Local Auth SDK for Windows Is not available | 4th Oct | 3 | Sprint 19 | 1 | Sprint 20 | Taleev
8 | Registration Client | Supervisor Authentication | MOS-28561, MOS-28538 | Medium | SDK | Tech5 | Not Yet Integrated | Local Auth SDK for Windows Is not available | 4th Oct | 1 | Sprint 19 | 1 | Sprint 20 | Taleev
9 | Registration Client | Local Biometric Deduplication | MOS-10555 | Medium | SDK | Tech5 | Not Developed | Local Auth SDK for Windows Is not available | 4th Oct | 3 | Sprint 19 | 3 | Sprint 20 | Sreekar
10 | Registration Client | Quality Score Calculation using MDS | MOS-1205, MOS-1291 | High |  |  | Dev Completed |  | NA | NA | NA | 2 | Sprint 19 | Sravan | Completed with SyncByte
11 | Registration Client | Quality Score Calculation using SDK | MOS-28656 | Medium | SDK | Tech5 | Not Yet Integrated | Quality Score Calculation SDK for Windows is not available | 4th Oct | 3 | Sprint 19 | 2 | Sprint 20 | Sreekar
12 | Registration Client | Scanner Integration | NA | High |  |  | Dev Completed | Device not available - Need More Clarity on RD Validation | NA | NA | NA | 2 | Sprint 19 | Ragav | Integrated with a Specific Model - Canon - K10402
13 | Registration Client | GPS Data Capture | NA | Low |  |  | Dev Completed | Device not available - Need More Clarity on Requierment | NA | NA | NA | 2 | Sprint 19 | Ragav | Integrated with a Specific Model - GPSBU343 (G-Start IV)
14 | Registration Client | QR Code Scanner Integration | MOS-29537, MOS-19014 | Low | Customer - to provide device |  | Not Developed | Device not available - Need More Clarity on Requierment | 4th Oct | 10 | Sprint 20 | 3 | Sprint 21 | Sreekar | Subject to Change as it is an Unknown
15 | Registration Client | Printer Integration | NA | Medium |  |  | Dev Completed | Device not available - Need More Clarity on RD Validation | NA | NA | NA | 2 | Sprint 19 | Usha | Integrated with Mindtree Configured Printer
16 | ID Authentication | MDM Integration | MOS-18214 | High | Device Vendor | SyncByte | In-Progress | Latest MDS is not available for encrypted data capture | 30th Sept | 5 | Sprint 19 | NA | TBD | Manoj
17 | ID Authentication | Single Finger Print Authentication | MOS-12072, MOS-28677 | High | Sl No. - 16 (MDS, SDK) | SyncByte, Tech5 | In-Progress | Issue - Vendor SDK only works in their Server | 1st Oct | 2 | Sprint 19 | 2 | TBD | Manoj
18 | ID Authentication | Multiple Finger Print Authentication | MOS-28783 | Medium | Sl No. - 16 (MDS, SDK) | SyncByte, Tech5 | In-Progress | Issue - Vendor SDK only works in their Server | 1st Oct | 2 | Sprint 19 | 2 | TBD | Manoj
19 | ID Authentication | Device Verification | MOS-21758 | High | Sl No. - 29 (Admin) |  | Not Developed | Admin APIs are not yet developed | 14th Oct | 8 | Sprint 20 | 2 | TBD | Loga
20 | ID Authentication | Iris Authentication | MOS-10308 | High | Sl No. - 16 (MDS, SDK) | SyncByte, Tech5 | Not Yet Integrated | Issue - Vendor SDK only works in their Server | 1st Oct | 4 | Sprint 20 | 2 | TBD | Manoj
21 | ID Authentication | Face Authentication | MOS-12073 | High | Sl No. - 16 (MDS, SDK) | SyncByte, Tech5 | Not Yet Integrated | Issue - Vendor SDK only works in their Server | 1st Oct | 4 | Sprint 20 | 2 | TBD | Manoj
22 | ID Authentication | Multifactor Authentication | MOS-28678, MOS-10831 | High | Sl No. - 19, 20, 21 (MDS, SDK) | SyncByte, Tech5 | Not Yet Integrated | Latest MDS is not available for encrypted data capture | 14th Oct | 2 | Sprint 20 | 2 | TBD | Loga
23 | ID Authentication | Internal Auth API | MOS-22416 | High | Sl No. - 22 (MDS, SDK) | SyncByte, Tech5 | Not Yet Integrated | Latest MDS is not available for encrypted data capture | 14th Oct | 2 | Sprint 20 | 2 | TBD | Manoj
24 | Registration Processor | Single ABIS Integration | MOS-28669, MOS-28668 | High | ABIS | Tech5 | In-Progress | Issue - Unable to use ABIS gallary Functionality Issue - Unable to Process Update Request in ABIS | 4th Oct | 2 | Sprint 19 | 2 | Sprint 20 | Girish | Mono : development done from reg-proc. Tech5 is yet to finish providing gallary match feature in their application. The estimation is for testing.
25 | Registration Processor | Multiple ABIS Integration | MOS-26089 | Low | Multiple ABIS | Tech5 Mantra Tech | Not Yet Integrated | Only one ABIS is available | 4th Oct | 7 | Sprint 20 | 4 | Sprint 21 | Girish | Mono : Estimation includes - - support to integrate with Mantratec ABIS. - Testing with multiple abis - Environment related changes (creating multiple queue instances to quickly switch between abis)
26 | Registration Processor | Device Verification | MOS-27829 | High | Sl No. - 29 (Admin) |  | Not Developed | Admin APIs are not yet developed | 14th Oct | 9 | Sprint 20 | 2 | Sprint 21 | Sowmya | New requirement. Estimation includes - - development - writing unit tests - developer test - system test
27 | Registration Processor | Integrating with Internal Auth API | MOS-28670 | High | Sl No. - 23 (IDA) |  | Not Yet Integrated | Internal Auth API is not developed due to Vendor dependency | 16th Oct | 1 | Sprint 20 | 1 | Sprint 21 | Girish | Mono : There would be no changes in reg-proc. Only testing would be required.
28 | Registration Processor | Quality Score Calculation using SDK | MOS-17610 | Medium | SDK | Tech5 | In-Progress | Issue - Vendor SDK only works in their Server | 4th Oct | 3 | Sprint 19 | 1 | Sprint 20 | Sowmya | Mono : development is done. We have tested deploying stage into tech5 VM. However end-to-end cant be tested until the sdk is bundled with docker container. Estimation is done for testing and defect fix.
29 | Admin | Device Provider Management | Refer Admin | High | Customer - Need Clarity |  | Not Developed | Requierment Detailing Pending |  | - |  | 1 |  |  | Available in Admin Sheet
30 | Registration Client | Adding Device in Packet | MOS-29293, MOS-28659 | High | Sl No. - 29 (Admin) |  | Not Developed | Admin APIs are not yet developed | 8th Oct | 4 | Sprint 20 | 1 | Sprint 21 | Taleev | Dependent on Spec of Admin
31 | Registration Processor | UI for Manual Verification | MOS-28672 | Medium | Customer - Need Clarity |  | Not Developed | Requierment Detailing Pending | 3rd Oct | 25 | TBD | 4 |  |  | Subject to Change as it is an Unknown

## Desirable Features
Sl No. | Modules | Features | Priority | Dependency | Vendor | Status | Status Comments | Dependency TBM By | Est.(Func Test) | Est. (CUT) | People | Comments
1 | Registration Client | UI for Device Status | Low | Customer |  | Not Developed
2 | Registration Client | Open JDK Intergation | Low | Customer |  | Not Developed
3 | Registration Client | First User Registration | Low | Customer |  | Not Developed
4 | Registration Processor | First User Registration | Low | Customer |  | Not Developed
5 | ID Repository | First User Registration | Low | Customer |  | Not Developed
6 | ID Repository | Storing FMR Record in ID Repository | Low | Customer, SDK |  | Not Developed
7 | Registration Processor | Change in ABIS API Spec | Low | Customer, ABIS |  | Not Developed
8 | Registration Processor | Multi-Partner ABIS - One ABIS Per Modality | Low | Customer, ABIS |  | Not Developed
9 | Registration Processor | Real Finger or Liveliness Check Identification | Low | Customer, SDK |  | Not Developed
10 | ID Authentication | Best Finger Detection | Low | Customer, SDK |  | Not Developed
11 | ID Authentication | Sending Signed Biometrics After Operator On Boarding | Low | Customer |  | Not Developed
12 | ID Authentication | ABIS 1:1 Authentication | Low | Customer, ABIS |  | Not Developed

## Legends
Priority | High | Medium | Low
Status | QA Completed | Dev Completed | In-Progress | Not Yet Integrated | Not Developed
Dependency TBM By | NA | Internal | Customer | Vendor