## Sheet1
Platform Document Components | Sub-Components | Assigned to | Current Status and ETA | % completion | CPU Approver | Additional Comment
1. INTRODUCTION | 1.1 Why-an Identity Management System is Needed | Lalana |  | 100 | Srijoni
| 1.2 Key Features of MOSIP Platform | Lalana |  | 100 | Srijoni
| 1.3 Key Objectives of MOSIP Platform | Lalana |  | 100 | Srijoni
2. FUNCTIONAL OVERVIEW | 2.1 Pre-Registration | Lalana |  | 100 | Krishnan
| 2.2 Registration Services | Lalana |  | 100 | Krishnan
| 2.3 Registration Processor | Lalana |  | 100 | Krishnan
| 2.4 ID Authentication | Lalana |  | 100 | Krishnan |  | LEGEND
| 2.5 Kernel | Lalana |  | 100 | Krishnan
| 2.6 Administration | Lalana |  | 100 | Krishnan |  |  | Complete
| 2.7 Resident Services | Lalana |  | 100 | Krishnan |  |  | WIP
| 2.8 Partner Management | Lalana |  | 100 | Krishnan |  |  | Yet to start
| 2.9 ID Repository | Lalana |  | 100 | Krishnan |  |  | Completed under review
3. Requirement Specification | 3.1 Functional Requirement Specifications | Lalana |  |  | Krishnan
| Pre-Registration |  |  | 100 | Krishnan
| Kernel |  |  | 100 | Krishnan
| IDA |  |  | 100 | Krishnan
| Reg-Processor |  |  | 100 | Krishnan
| Resident Services |  | 2019-07-31 | 50 | Krishnan
| Reg Client |  |  | 100 | Krishnan
| Administrator Services |  | 2019-07-31 | 20 | Krishnan
| Partner Management |  | 2019-07-31 | 10 | Krishnan
| 3.2 Non-Functional Requirement Specifications | Lalana\Shravan | 2019-07-31 | 10 | Krishnan
6. PRODUCT DEMO (VDs) |  | Resham\Krishnan | TBD |  | Krishnan
4. ARCHITECTURE OVERVIEW | 4.1 Principles | Shravan |  | 100 | Ramesh
| 4.2 Platform Features |  |  |  | Ramesh
| 4.2.1 Configurability | Shravan |  | 100 | Anadi
| 4.2.2 Extensibility | Shravan |  | 100 | Anadi
| 4.2.3 Modularity | Shravan |  | 100 | Anadi
| 4.3 Process View | MOSIP BA |  | 50 | Shrikant
| 4.3 Logical View | Shravan |  | 100 | Anadi
| 4.4 Technology Stack | Shravan |  | 100 | Anadi
| 4.5 Data Architecture | Shravan |  | 100 | Anadi
5. ARCHITECTURALLY SIGNIFICANT COMPONENTS | 5.1 ID Object Definition | Shravan |  | 100 | Ramesh
| 5.2 Configurations | Shravan |  | 100 | Ramesh
| 5.3 Registration Packet Structure | Shravan |  | 100 | Ramesh
| 5.4 ABIS middleware | Shravan |  | 100 | Ramesh
| 5.5 Biometric Data Standards | Shravan |  | 100 | Ramesh
| 5.6 MOSIP Device Specifications | Shravan |  | 100 | Ramesh
| 5.7 Core Data Management | Gurpreet |  | 100 | Ramesh
| 5.8 Integration with External System | Sanjay Shivaji Zende |  | 100 | Ramesh
6. TEST RIG | 6. TEST RIG | Gita et al | 2019-07-31 | 40 | Krishnan
7. PERFORMANCE AND SIZING GUIDELINES | 7. PERFORMANCE AND SIZING GUIDELINES | Lalana\Shravan | 2019-07-31 | 60 | Krishnan
8. Privacy And Security | 8. Privacy And Security | Shravan\John |  | 100 | Sasi
9. MOSIP APIs | 9.1 External APIs
| 9.1.1 ID Authentication APIs | Gurpreet |  | 100 | Ramesh
| 9.1.2 ABIS APIs | Sanjay Shivaji Zende |  | 100 | Ramesh
| 9.1.3 OTP Manager API | John |  | 100 | Ramesh
| 9.1.4 Pre-Registration APIs | Ravi Chitragar Balaji |  | 100 | Ramesh
| 9.1.5 Registration Processor APIs | Sanjay Shivaji Zende |  | 100 | Ramesh
9.2 Internal APIs
| 9.2.1 Kernel | John |  | 100 | Ramesh
| 9.2.2 ID Repository | Gurpreet |  | 100 | Ramesh
| Administrator Services APIs | John | 2019-07-31 | 0 | Ramesh | The APIs are yet to be identified
| Resident Services APIs | John | 2019-07-31 | 0 | Ramesh | The APIs are yet to be identified
| Partner management APIs | Sachin | 2019-07-31 | 0 | Ramesh | The APIs are yet to be identified
10.BUILDING AND DEPLOYING MOSIP (TBD) | 10.1 Getting Started Guide
| Getting the Source Code | Ajith\Swati Raj | 2019-06-30 | 50 | Anand
| Setup and Configure Jenkins | Ajith\Swati Raj | 2019-06-30 | 50 | Anand
| Setup and Configure Jfrog | Ajith\Swati Raj | 2019-06-30 | 50 | Anand
| Setup and Configure SonarQube | Mohan | 2019-06-30 | 50 | Anand
| Setup and Configure Docker Registry | Ajith\Swati Raj | 2019-06-30 | 50 | Anand
| Installing External Dependencies | Mohan | 2019-06-30 | 50 | Anand
| Configuring MOSIP | Ajith\Swati Raj | 2019-06-30 | 50 | Anand
| MOSIP Deployment | Ajith\Swati Raj | 2019-06-30 | 50 | Anand
10.2 Developer Document
| MOSIP Configuration Server | John |  | 100 | Ramesh
| MOSIP REST API Guidelines | John |  | 100 | Ramesh
| MOSIP Java Coding Standards | John |  | 100 | Ramesh
| MOSIP Best practices of Git | John |  | 100 | Ramesh
| Eclipse Markdown Editor | John |  | 100 | Ramesh
| Auth Implementation | Ramadurai Saravana Pandian <Ramadurai.Pandian@mindtree.com> |  | 100 | Ramesh
| 10.3 Customization | Shravan | 2019-07-31 | 0 | TBD | TBD after performance testing
11. INFRASTRUCTURE RECOMMENDATIONS | 11.1 Data Center Architecture | Shravan | 2019-07-31 | 0 | TBD
12. GLOSSARY | 12. GLOSSARY | TBD | 2019-06-10
13. ABBREVIATIONS | 13. ABBREVIATIONS | TBD | 2019-06-10
14. REFERENCES | 14. REFERENCES | TBD | 2019-06-10
15.TROUBLESHOOTING | 15.TROUBLESHOOTING | TBD | TBD
Note on A1: Windows User: As per the agreed TOC with Client
Note on A87: Windows User: TBD after performance testing