## Story List
Addendum user stories to be created
Base story ID | Feature | Changes
Sprint 2
MOS-14 | Download client
MOS-61 | Launch
MOS-64 | Create packet
MOS-65 | Encrypt packet
Sprint 3
MOS-553 | Login with pw or OTP
MOS-563 | Logout
MOS-335 | Copy address
MOS-338 | Print receipt
MOS-556 | View packets for approval
MOS-558 | Approve packets
MOS-554 | Validate packet data
MOS-559 | Push packets
Sprint 4

## Changes
Addendum user stories to be created
S No | Module name | Changes to be made | Estimate
1 | Document upload | Only one file per document will be supported.Generate the scanned output in pdf format and merge the new content to the existing document. | 15
2 | Pre-reg packet deletion | Delete pre-reg packet if not consumed in client after 15 days of appointment date. | 4
3 | Demographic data | 'Foreigner' field should be added. In the back end, Applicant Type attribute should contain 'Citizen-Child', 'Foreigner-Child', 'Citizen-Adult' or 'Foreigner-Adult'. | 4
4 | Reg packet upload | If client is online, packet should be uploaded on creation provided EoD process is turned off. Job creation for frequently check status and push packet | 15
5 | Opt to register | If packet is not approved beyond x hrs from date of registration or if more than x packets are queued for EoD clearance, system should freeze the registration client for new registrations.eod on/ off flag also should be validated. | 5
6 | Login | Super admin should login using multifactor mode.Existing to be changed to accommodate. Login screen,EOD process,authentication to be aligned to 1.17 ppt. | 15
7 | Reg packet upload | 'Export' feature is removed from scope. | Discussion required
8 | Demographic data | Upon entering pre-registration ID, 1. Check if data exists in local database. 2. If yes, check if an updated pre-reg is available on the server. 3. If yes, download from the server and pre-populate on screen. 4. If update not available on server, display data from local database. 5. If data not available in local database, do not pre-populate on screen. Design change | 4